## Activities List
S. No. | Day | Modules | Sub Activity | Owner | Pre-requisites | Completion Status
1 |  | Registration & Maid Tagging
| 0 |  | Creation of RWA Dashboard and configuration of Address | Servizing Ops Team with inputs from RWA | Provide details of user which will have have full access to the Servizing Dashboard including access to Resident details
| 0 |  | Creation of Service Providers Data Roles (RWA Helper/Security Supervisor) | Servizing Ops Team with inputs from RWA | Details needed from RWA team
| 0 |  | Updation of Maids/Helpers/Drivers/Cook/Gardener, etc. data on Servizing Portal | RWA Helper Role User | Android Phone with internet(sim not needed)
| 0 |  | Generation of Helper Identity Card | RWA Helper Role User | None
| 0 |  | Activation of Online Payment Module | Servizing & Rank One Team | None |  | Ashu needs to come back with anhy issues being faced in the current portal | 2022-06-15
|  |  | Bringing all Payment and Maintenance module online | Servizing & Rank One Team | None
| 0 |  | Association of maid to RWA Office | Servizing Team - Ops | Authorisation from RWA team
| 1 |  | Training of scanning at Gate | Security Supervisor Role | Android Phone with internet(no sim needed)
| 1 |  | Warm up message to Residents about all the activities that will start soon. Notify about gate management, helper management, service center, communication center and much more…. | RWA Team + Servizing Info Team | None
| 1 |  | Handover to shift guards about scanning | Security Supervisor Role | None
| 2 |  | Scanning Monitoring at Gate | Security Supervisor + Serviizing Ops | None
| 3 |  | Identification of Maids with no identity cards + Scanning continued | RWA Helper Role User | None
| 4 |  | Scanning continued + distribution of cards to remaining helpers | RWA Helper Role User | None
| 5 |  | Scanning + Monitoring | Security Supervisor Role | None
| 5 |  | Configuration verification of switches of Servizing before notification to Residents(Critical) - Enablement of Maids, Helper tagging, Notification Center, Yellow Pages, Polls to be activated | Servizing Ops Team with inputs from RWA | None
| 6 |  | Download, registration open for RWA members, their family and close friends(as a resident) | RWA Team | None
| 7 |  | Notification to Residents about registration on Servizing apps and tag their maids. Distribution of hard copies at every door. This should happen on Saturday morning | RWA Team + Servizing Info Team | None
| 8 |  | Standee at main gate with QR link to download the app | RWA Team + Servizing Info Team | None
| 9 |  | Monitoring of Registration & Tagging reports daily | Servizing Team - Ops | None
| 9 |  | Send soft copy of common area helpers and common services QRs to residents group. | RWA Team + Servizing Info Team | None
| 9-18 days |  | Tagging status | Servizing Team - Ops | None
| 19th day |  | Notify residents about stoppage of untagged maids at gate | RWA Teams | None
| 22nd Day |  | Untag maids from RWA Office | Servizing Team - Ops | Authorisation from RWA team
| 23rd Day |  | Suggest access denied maids to get their ID card tagged via blue cards | Security Supervisor Role | Blue Cards content |  | Untagged maid red cards
| 27th Day |  | Red card to untagged maids | Security Supervisor Role | Red Card Content
| 30th Day |  | Access Denials to unregistered maids | Security Supervisor Role | None
| 19th Day | Service Center | Set Up Service Center roles and responsibilites with Switch Off | Servizing Team - Ops | Inputs from Estate Manager
| 19th Day |  | List of all the Service Providers | Servizing Team - Ops with Estate Management Team | None
| 20th Day |  | Training of Service Management | Servizing Team - Ops with Estate Management Team | None
| 21st Day |  | Training of Service Management | Servizing Team - Ops with Estate Management Team | None
| 22nd Day |  | Training of Service Management | Servizing Team - Ops with Estate Management Team | None
| 23rd Day |  | Demonstration of Service Center | Servizing Team - Ops with Estate Management Team | None
| 24th Day |  | Switch on Service Center | Servizing Ops Team with inputs from RWA | None
| 25th Day |  | Monitoring of Service Center SLA and tracking of services | Servizing Team - Ops with Estate Management Team | None
| 26th Day 30th Day |  | Observation of delayed services and unauthorised maids entry | Servizing Team - Ops with Estate Management Team + RWA | None
| 19th Day | Self Vehicle Management | Configure max number of 2 wheeler 4 wheeler passes | Servizing Ops Team with inputs from RWA | None
| 20th Day |  | Notify Residents about Vehicle Registration after enablng the switch | RWA Team + Servizing Info Team | None
| 23rd Day |  | Follow up with Residents before first batch of Resident's vehicle sticker is issued | Servizing Ops Team with inputs from RWA | None
| 25th Day |  | Print first batch of stickers for vehicle's | Estate Management Team | None
| 26th Day |  | Advice gate to recommend resident to register their vehicle when they no pass on their vehicles | Security Supervisor Role | None
| 31st Day |  | Print second batch of vehicles | Estate Management Team | None
| 35th day |  | Advice residents to get their vehicle registered before last round of batch printing of passes | RWA Team | None
| 40th Day |  | Issue last batch printing | Estate Management Team | None
| 31st Day | Visitor Management | Improvement of Main gate infra team and partitioning of guests/resident using cone(manual) | Security Supervisor + Serviizing Ops + RWA | None
| 32nd Day |  | Improvement of Main gate infra team and partitioning of guests/resident using cone(manual) | Security Supervisor + Serviizing Ops + RWA | None
| 34th Day |  | Deployment of Servizing Controllers at gate + 2 Phones Android with Sim card | Security Supervisor + Serviizing Ops + RWA | Servizing Controllers Procuremen + 2 Android Phone with Sim card
| 35 - 39th Day |  | Enable switch for visitor management at non - peak hours and train guards | Security Supervisor + Serviizing Ops | None
| 40th Day |  | Notify residents about enablement of visitor management system from 12am onwards | RWA Team + Servizing Info Team | None
| 41st Day |  | Enablement of gate mgmt switch | Servizing Ops Team with inputs from RWA | None
| 42nd - 50th Day |  | Observation of gate logs | Security Supervisor + Serviizing Ops | None
| 42nd Day |  | Update the rule of incorrect parking workflows to residents | RWA Team | None
| Parallel Activities |  | Automation of gate of pedestrian | Servizing Hardware Team | Same controller can be used/turnstile/iron mesh door, etc can be installed as per RWA choice)